## Sheet1
date | block1: | block2: | block3: | block4: | task | time | assigned | check | extra
2020-02-01 | make character | manufactorer backstory | make manufactorers | draw melee parts | make character | 2 | 2 | TRUE | class and information
2020-02-02 | draw melee parts | manufactorer backstory | make manufactorers | draw melee parts | draw melee parts | 10 | 12 | FALSE | 25 per part
2020-02-03 | work out projectile class and parts | make controls | work out projectile class and parts | draw melee parts | draw character | 4 | 4 | TRUE | all frames
2020-02-04 | make controls | make inventory class | make inventory interface | draw melee parts | make manufactorers | 6 | 4 | FALSE | classes min 4 man
2020-02-05 | make inventory class | make inventory interface | tidy up project | draw melee parts | manufactorer backstory | 4 | 4 | TRUE | make a narative
2020-02-06 | design level structure | weapon balance |  | draw projectile parts | draw projectile parts | 10 | 10 | TRUE | 20 per part
2020-02-07 | design level structure | weapon balance |  | draw projectile parts | work out projectile class and parts | 4 | 4 | TRUE | create the parts and workable case
2020-02-08 | design level structure | design enemies | story building | draw projectile parts | make controls | 4 | 4 | TRUE | create character and game controls
2020-02-09 |  |  |  | draw projectile parts | make inventory class | 4 | 4 | TRUE | create class for saving weapons
2020-02-10 | design enemies | story building |  | draw projectile parts | make inventory interface | 4 | 4 | TRUE | make interface to see the inventory
2020-02-11 |  | design enemies | tidy up project | draw character | draw background and images | 6 | 6 | TRUE | backgroud texture and images to be in the background
2020-02-12 | figure out animating | figure out animating |  | draw character | design level structure | 6 | 6 | TRUE | think of ways to make levels or ways to play the game continious or run based etc.
2020-02-13 | draw enemies |  |  | draw background and images | weapon balance | 4 | 4 | TRUE | see what can be done to balance weapons and parts
2020-02-14 | draw enemies |  |  | draw background and images | design enemies | 6 | 6 | TRUE | design enemy classes and deriving
2020-02-15 | draw enemies |  |  | draw background and images | draw enemies | 2 | 10 | 20 | draw enemies in all frames./per enemy
2020-02-16 | draw enemies |  |  | draw enemies | figure out animating | 4 | 4 | TRUE | see what pygame offers for animating something using a series of pictures.
[5 empty] | tidy up project | 2 | 4 | 8 | /at a time
[5 empty] | story building | 4 | 4 | TRUE
[5 empty] | make a leveling system | 4 | 0 | FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE